## Subject to Approval Projects
CURRENT PROJECTS SUBJECT TO APPROVAL |  | MILESTONES | [12 empty] | DETAILS
PROJECT NAME | DESCRIPTION | PRESENTED TO BOARD | RETAINER SIGNED | RETAINER FUNDED | CONDITION STUDY | FINAL PLAN/IMPACT | BUDGET | PLANNING | PPLD IA | PPLD | BOCC | SEWCD | SCHOOL DISTRICT | CITY COUNCIL | NOTES
AMALGRE/LOFTS @ 1609 | Affordable Housing S/E | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-11-01 | 2021-02-01 | 2021-06-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | Nov | 2021-11-21 | 2021-12-21 | CLOSED!!!!!!!!!!!!!!!!!!!
HANCOCK COMMONS | Attainable Housing w/Commercial S/E | 2021-04-01 | 2021-05-01 | 2021-05-01 | 2021-06-01 | 2021-08-21 | 2022-10-22 | 2022-12-22 | 2022-10-22 | 2022-10-22 | 2022-12-22 | 2023-01-23 | 2022-06-22 | Jan/23 Feb/23 | Dealing with a CMR's issue with project and PPRTA
WEIDNER / CITYGATE | Market Rate Housing w/Commercial Downtown | 2021-04-01 | 2021-06-01 | 2021-07-01 | 2021-09-21 | 2021-11-21 | 2022-10-22 | 2022-11-22 | 2022-10-22 | 2022-12-22 | 2022-05-22 | 2023-01-23 | 2022-05-22 | Jan/23 Feb/23 | Council Vote March 14
GAZETTE SF | Market Rate Housing w/Commercial Downtown | 2021-04-01 | [12 empty] | Project on hold at this point with no updates
Gold Hill Commerical | Commercial/Residential development in GHM | 2021-08-21 | 2022-12-21 | 2022-12-21 | 2022-02-22 | 2022-04-22 | 2022-11-22 | 2023-02-23 | 2022-10-22 | 2022-11-22 | 2022-02-23 | 2022-01-23 | 2022-12-22 | Jan/23 Feb/23 | MOU complete with school district. Council vote March 14
Park Union | Boundary expansion and new area | 2022-12-21 | 2022-02-21 | 2021-01-01 | 2022-02-22 | [9 empty] | No New updates
Oneil Project | Office/residential project with retail | 2022-10-21 | 2022-12-21 | 2022-08-22 | 2022-08-22 | [9 empty] | No New updates
Lowell Draper | Downtown attainable housing project | 2022-07-22 | [12 empty] | Once retainer is funded we're ready to start back up
Project Garnet |  | 2023-01-23 |  |  | 2023-12-22 | 2023-12-22 | N/A | 2023-01-23 | N/A | N/A | 2023-02-23 | 2023-01-23 | 2023-02-23 | 2023-02-23 | Developer agreement signatures is final step.

## Current Projects
URA | PROJECT | START | END |  | CONSTRUCTION | PROJECT COMPLETION | NOTES
C4C PROJECTS | AFA Visitor Center |  |  | In Progress | Started | 2024 | Construction is Commenced
| Robson Arena |  |  | Complete | Complete | Complete
| Weidner Field |  |  | Complete | Complete | Complete
| USOPM |  |  | Complete | Complete | Complete
| Hybyl Sports Medicine |  |  | Complete | Complete | Complete
MUSEUM & PARK | Residential & Commercial | 2018 | 2043 | Bonds Issued | Infrastructure/Streetscape | TBD | Developer Proceeding with a New Area/Clock. Streetscape/Bridge won the ULI impact reward
CITY AUD BLOCK | Hyatt Hotel | 2004 | 2029 | Complete | OPEN! | Fall 2021 | URA signed agreement to work with city and developers on new plan for transit center. SOM selected as architect and design firm!
GOLD HILL MESA | Residential | 2004 | 2029 | Complete | In Progress | Fall 2021 | Amendment to boundary area in front of districts as they approve commercial
| Commercial | 2015 | 2040 | No | In Progress | TBD | Currently in the new plan start process
IVYWILD |  | 2011 | 2036 | Complete | Complete | Complete*
N. NEVADA AVE |  | 2015 | 2040 | Complete | Complete* | Complete* | Still waiting for Lexus to commence.
POLARIS POINTE |  | 2010 | 2035 | Complete | In Progress | Fall 2021/Spring 2022 | Amplitheater passes Council
TEJON & COSTILLA |  | 2018 | 2043 | Complete | In Progress | Spring 2022 | Opened and doing great!
TRUE NORTH COMMONS |  | 2019 | 2044 | No (see AFA) | In Progress | TBD | Under Construction
VINEYARD |  | 2011 | 2036 | Complete | Complete* | Complete* | In front of board today
S. NEVADA | EVC-HD |  |  | Complete | Complete | Complete | Developer has shown interest in securing other sites on east side if TIF available.
| Ivywild LLC |  |  | Complete | In Progress | Late 2024 (estimated) | Have met with Hotel team to discuss new timelines
| Canyon Creek LLC |  |  | Ongoing | In Progress | Late 2024 (estimated) | Council passed sales tax increase to 2% Heavy site work and creek work Danny is working on adding in apartments