## Museum
PROJECT ELEMENT |  | PROJECT STATUS
US Olympic Museum & Hall of Fame
Deliverable |  |  | Completion
Number | Deliverable Description | Status | Date
OM-01 | Commencement of Substantial Work | Design contracts were executed for the Programming and Concept Design phases. Full design contracts have been executed in the 3rd quarter of 2015. | 2015-07-02
OM-02 | Satisfy Minimum Size Requirements | The conceptual design meets minimum size requirements
OM-03, 04 | Cooperation Agreement with Financing Entity | Agreements have been executed and approved by EDC | 2015-07-22
OM -05 | Long Term License Agreement w/USOC | Complete as of signature of EDC Resolution.
Om-06 | Exhibit Agreement w/USOC | Complete as of signature of EDC Resolution.
OM- 07 | Shuttle Service Feasibility Study
OM-08 | USOC Agreement (SectionF) | Complete as of signature of EDC Resolution.
OM-09 | Hall of Fame w/Summer, Winter, Para Exhibits | World-class Exhibit Designer Selected. Designs Initiated.
OM-10 | Iconic Design, World Class Facility | World class Architect Selected. Design ongoing.
w/State of the Art Technology
OM-11 | SW Downtown Infrastructure (Exhibit B)
OM-12 | Project Element Placed in Service

## Event Ctr
PROJECT ELEMENT |  | PROJECT STATUS
Colorado Sports and Event Center
Deliverable |  |  | Completion
Number | Deliverable Description | Status | Date
SC-01 | Commencement of Substantial Work
SC-02 | Satisfy minimum Size Requirements
SC-03, 04 | Cooperation Agreement with Financing Entity | Draft Agreement is being revised as per EDC legal review
SC-05 | Business Plan
SC-06 | SW Downtown Infrastructure
SC- 07 | Project Element Placed in Service

## UCCS
PROJECT ELEMENT |  | PROJECT STATUS
UCCS Sports Medicine & Performance Center
Deliverable |  |  | Completion
Number | Deliverable Description | Status | Date
MP-01 | Commencement of Substantial Work | Detailed building program and infrastructure planning continues
MP-02 | Satisfy Minimum Size Requirements
MP-03, 04 | Cooperation Agreement with Financing Entity | Agreement has been executed and approved by EDC
MP-05 | Certify Pro Relationships w/10 Organizations | 11 Letters have been obtained to date by UCCS
dedicated to US Armed Forces Vet. Recovery
MP-06 | Clinical Space Requirements
Certified Requirements of Section J met
MP-07 | Centers for Excellence in 3 Disciplines
Certified Requirements of Section J met
MP 07 | Project Element Placed in Service

## USAFA
PROJECT ELEMENT |  | PROJECT STATUS
U.S. Air Force Academy Gateway Visitor's Center
Deliverable |  |  | Completion
Number | Deliverable Description | Status | Date
AF-01 | Commencement of Substantial Work | Project development continues. Substantial work projected to begin | Fall 2016
Fall of 2016
AF-02 | Satisfy Minimum Size Requirements | N/A this quarter
AF-03, 04 | Cooperation Agreement with Financing Entity | Draft Agreement under review by USAFA & OEDIT
AF- 05 | Project Element Placed in Service | N/A this quarter

## City
PROJECT ELEMENT |  | PROJECT STATUS
City of Colorado Springs - Applicant
Deliverable |  |  | Completion
Number | Deliverable Description | Status | Date
CS-01 | Create a Stadium Authority
CS-02 | Create a Regional Tourism Advisory Board
CS-03 | Cooperation Agreement with Financing Entity | Agreement has been executed and approved by EDC
CS-04 | Propreitary Information Designated

## CSURA
PROJECT ELEMENT |  | PROJECT STATUS
Financing Entity: Colorado Springs Urban Renewal Authority
Deliverable |  |  | Completion
Number | Deliverable Description | Status | Date
FE-01 | Quarterly Report Submitted to EDC | Q2 2015 submitted | 2015-07-27
FE-02, 03 | Quarterly Meeting w/Director | Q2meeting completed (conference call) | 2015-08-01
FE-04 | Semi Annual Progress Meeting w/EDC | Completed on 6/11/15 | 2015-06-11
FE-05 | Annual Reports & Audits Submitted to EDC | Being prepared - Independent Auditor to be selected
FE-06 | Business List in RTA Zone Submitted | Finalized by DOR under review by City of Colorado Springs
FE-07 | Propreitary Information Designated
FE-08 | Notification of Consolidation or Refinancing
Provided to EDC
FE-09 | Bond Documents provided to EDC
Bond Counsel Opinion
FE-10 | Privately Placed Bonds Issued
Interest Accruing
FE-11 | Sub-Accounts Pledged to Bond & Amounts
FE-12 | Bond Proceed Sub-Accounts Established
FE-13 | Bond Proceed Accounts Porportionate to the
Dedicated Revenue from Element sub-account
FE-14 | Portion of Proceeds used for USAFA Center
FE15 | Director Notified of Sub-Accounts for Bonds
Amount Pledged per Account
FE-16 | EDC Approval of Division of Bond Proceeds
Between Project Elements
FE-17 | Financing Entity Certification of Eligible Costs
FE-18 | Cooperation Agreements w/Project Elements | Complete except for AFA Visitor Center to be approved 10/28/15
FE-19 | Engineering Certification of Consruction Costs
FE-20 | Engineering Certif.of Plans and Construction
as per Exhibit B, Section 5
FE-21 | CPA Certification of Eligible Costs
FE-22 | CPA Certification of funds expended from
Sub-Accounts used for Project Elements
FE-23 | Contractor selection in accordance with Federal
State and Local procurement Laws
FE-24 | External Advisor Certification of interest and
Financing Costs
Fe-25 | Dedicated Revenue Sub-Divided into 5 | Established by CLA
Sub-Accounts as per MEAP's